## Excavation
|  | Constants |  |  |  |  | Number of workers
Activity | Quantity (m3) | Mate | Mazdoor | Bhisti | Mixer | Mixer operator | Mate | Mazdoor | Bhisti | Mixer | Mixer operator | Mate | Mazdoor | Bhisti | Mixer | Mixer operator
Excavation | 98.057 | 0.06 | 0.62 |  |  |  | 5.8834 | 60.7953 |  |  |  | 6 | 61 | 0
Bacfilling | 159.3495 | 0.02 | 0.25 | 0.02 |  |  | 3.187 | 39.8374 | 3.187 |  |  | 4 | 40 | 4

## R_C_C
|  | Constants | [5 empty] | Number of workers
Activity | Quantity (m3) | Mate | Mazdoor | Bhisti | Mixer | Mixer operator | Vibrator | Mate | Mazdoor | Bhisti | Mixer | Mixer operator | Vibrator | Mate | Mazdoor | Bhisti | Mixer | Mixer operator | Vibrator
Footing PCC | 2.6232 | 0.1 | 1.63 | 0.7 | 0.07 | 0.07 | 0.07 | 0.26232 | 4.2759 | 1.8363 | 0.18363 | 0.18363 | 0.18363 | 1 | 5 | 2 | 1 | 1 | 1
Footing RCC | 4.1883 | 0.17 | 2 | 0.9 | 0.07 | 0.07 | 0.07 | 0.71201 | 8.3766 | 3.7695 | 0.29318 | 0.29318 | 0.29318 | 1 | 9 | 4 | 1 | 1 | 1
Plinth beam rcc | 4.994 | 0.2 | 3 | 0.9 | 0.07 | 0.07 | 0.07 | 0.9988 | 14.982 | 4.4946 | 0.34958 | 0.34958 | 0.34958 | 1 | 15 | 5 | 1 | 1 | 1
total column rcc upto 2 floor | 8.6983 | 0.23 | 3.5 | 0.9 | 0.1 | 0.1 | 0.1 | 2.0006 | 30.444 | 7.8285 | 0.86983 | 0.86983 | 0.86983 | 3 | 31 | 8 | 1 | 1 | 1
For Ground Floor and first floor beam Beam | 3.8138 | 0.2 | 3 | 0.9 | 0.07 | 0.07 | 0.07 | 0.76276 | 11.4414 | 3.4324 | 0.26697 | 0.26697 | 0.26697 | 1 | 12 | 4 | 1 | 1 | 1
secindfloor beqams + slabs RCC | 47.7092 | 0.2 | 3 | 0.9 | 0.07 | 0.07 | 0.07 | 9.5418 | 143.1276 | 42.9383 | 3.3396 | 3.3396 | 3.3396 | 10 | 144 | 43 | 4 | 4 | 4
Lintel RCC | 1.3999 | 0.2 | 3 | 0.9 | 0.07 | 0.07 | 0.07 | 0.27998 | 4.1998 | 1.2599 | 0.097995 | 0.097995 | 0.097995 | 1 | 5 | 2 | 1 | 1 | 1
| Mate | Mazdoor | Bhisti | Mixer | Mixer operator | Vibrator
Footing PCC | 1 | 5 | 2 | 1 | 1 | 1
Footing RCC | 1 | 9 | 4 | 1 | 1 | 1
Plinth beam rcc | 1 | 15 | 5 | 1 | 1 | 1
total column rcc upto 2 floor | 3 | 31 | 8 | 1 | 1 | 1
For Ground Floor and first floor beam Beam | 1 | 12 | 4 | 1 | 1 | 1
secindfloor beqams + slabs RCC | 10 | 144 | 43 | 4 | 4 | 4
Lintel RCC | 1 | 5 | 2 | 1 | 1 | 1
| 10 | 144 | 43 | 4 | 4 | 4
| 5 | 72 | 21.5 | 2 | 2 | 2

## Formwork
|  | Constants | [6 empty] | Number of workers
Activity | Quantity (m2) | Mate | Mazdoor | Bhisti | Mixer | Mixer operator | Capenter | Barbender | Mate | Mazdoor | Bhisti | Mixer | Mixer operator | Carpenter | Mate | Mazdoor | Bhisti | Mixer | Mixer operator | Carpenter
Footing | 27.391 |  | 0.2 |  |  |  | 0.25 |  |  | 5.4782 | 0 | 0 | 0 | 6.8477 | 0 | 6 | 0 | 0 | 0 | 7
Column (total) | 152.01 |  | 0.2 |  |  |  | 0.25 |  |  | 30.402 | 0 | 0 | 0 | 38.0025 | 0 | 31 | 0 | 0 | 0 | 39
beams plinth | 39.6 |  | 0.2 |  |  |  | 0.3 |  |  | 7.92 | 0 | 0 | 0 | 11.88 | 0 | 8 | 0 | 0 | 0 | 12
beams ground and first | 77.28 |  | 0.2 |  |  |  | 0.3 |  |  | 15.456 | 0 | 0 | 0 | 23.184 | 0 | 16 | 0 | 0 | 0 | 24
beams second | 8.344 |  | 0.2 |  |  |  | 0.3 |  |  | 1.6688 | 0 | 0 | 0 | 2.5032 | 0 | 2 | 0 | 0 | 0 | 3
Slab (2) | 211.801 |  | 0.2 |  |  |  | 0.23 |  |  | 42.3602 | 0 | 0 | 0 | 48.7142 | 0 | 43 | 0 | 0 | 0 | 49
Balcony | 9.26 |  | 0.2 |  |  |  | 0.3 |  |  | 1.852 | 0 | 0 | 0 | 2.778 | 0 | 2 | 0 | 0 | 0 | 3
Terrace | 28.762 |  | 0.2 |  |  |  | 0.23 |  |  | 5.7524 | 0 | 0 | 0 | 6.6153 | 0 | 6 | 0 | 0 | 0 | 7
Mumty Terrace | 17.68 |  | 0.2 |  |  |  | 0.23 |  |  | 3.536 | 0 | 0 | 0 | 4.0664 | 0 | 4 | 0 | 0 | 0 | 5
| Mate | Mazdoor | Bhisti | Mixer | Mixer operator | Carpenter
Footing | 0 | 6 | 0 | 0 | 0 | 7
Column (total) | 0 | 31 | 0 | 0 | 0 | 39
beams plinth | 0 | 8 | 0 | 0 | 0 | 12
beams ground and first | 0 | 16 | 0 | 0 | 0 | 24
beams second | 0 | 2 | 0 | 0 | 0 | 3
Slab (2) | 0 | 43 | 0 | 0 | 0 | 49
Balcony | 0 | 2 | 0 | 0 | 0 | 3
Terrace | 0 | 6 | 0 | 0 | 0 | 7
Mumty Terrace | 0 | 4 | 0 | 0 | 0 | 5

## Brickwork
|  | Constants |  |  |  |  | Number of workers
Activity | Quantity (m3) | Mate | Mazdoor | Bhisti | Mixer | Mixer operator | Mate | Mazdoor | Bhisti | Mixer | Mixer operator | Mate | Mazdoor | Bhisti | Mixer | Mixer operator
Groundfloor | 39.468 | 0.25 | 0.4 | 0.1 |  |  | 9.867 | 15.7872 | 3.9468 |  |  | 10 | 16 | 4 | 0
First floor | 44.821 | 0.25 | 0.4 | 0.1 |  |  | 11.2052 | 17.9284 | 4.4821 |  |  | 12 | 18 | 5 | 0
Secondfloor | 13.319 | 0.25 | 0.4 | 0.1 |  |  | 3.3298 | 5.3276 | 1.3319 |  |  | 4 | 6 | 2 | 0
Below plinth | 16.93 | 0.25 | 0.4 | 0.1 |  |  | 4.2325 | 6.772 | 1.693 |  |  | 5 | 7 | 2 | 0

## Plastering and painting
|  | Constants | [5 empty] | Number of workers
Activity | Quantity (m2) | Mate | Mazdoor | Bhisti | Mixer | Painter | Mixer operator | Mate | Mazdoor | Bhisti | Mixer | Painter | Mixer operator | Mate | Mazdoor | Bhisti | Mixer | Painter | Mixer operator
Groundfloor walls | 397.8 | 0.06 | 0.1 | 0.1 |  | 0.35 |  | 23.868 | 39.78 | 39.78 | 0 | 139.23 |  | 24 | 40 | 40 | 0 | 140 | 0
First floor walls | 478.32 | 0.06 | 0.1 | 0.1 |  | 0.35 |  | 28.6992 | 47.832 | 47.832 | 0 | 167.412 |  | 29 | 48 | 48 | 0 | 168 | 0
Secondfloor wall | 138.008 | 0.06 | 0.1 | 0.1 |  | 0.35 |  | 8.2805 | 13.8008 | 13.8008 | 0 | 48.3028 |  | 9 | 14 | 14 | 0 | 49 | 0
Wall below plint | 73.6 | 0.06 | 0.1 | 0.1 |  | 0.35 |  | 4.416 | 7.36 | 7.36 | 0 | 25.76 |  | 5 | 8 | 8 | 0 | 26 | 0
Groundfloor ceiling | 88.753 | 0.06 | 0.1 | 0.1 |  | 0.35 |  | 5.3252 | 8.8753 | 8.8753 | 0 | 31.0635 |  | 6 | 9 | 9 | 0 | 32 | 0
First floor ceiling | 88.315 | 0.06 | 0.1 | 0.1 |  | 0.35 |  | 5.2989 | 8.8315 | 8.8315 | 0 | 30.9102 |  | 6 | 9 | 9 | 0 | 31 | 0
secondfloor ceiling | 38.596 | 0.06 | 0.1 | 0.1 |  | 0.35 |  | 2.3158 | 3.8596 | 3.8596 | 0 | 13.5086 |  | 3 | 4 | 4 | 0 | 14 | 0
Floor laying | 215.64 | 0.12 | 0.2 | 0.1 |  | 0.35 |  | 25.8768 | 43.128 | 21.564 |  |  |  | 26 | 44 | 22 | 0 | 0 | 0
Flor polishing